## Projected statistics 2024 - 29
Lao PR Workplan 1st August 2024 to 31st July 2030
|  | Humanitarian clearance (ha) | Total Clearance (Humanitarian and Commercial) (ha) | Total Ordnance Destroyed | Total Cluster Munitions Destroyed | Technical Survey (CMRS) completed (ha) | Non-Technical Survey completed (villages) | Risk Education completed (beneficiaries)
2025 | Total (from 1st August) | 2708.3333 | 2916.6667 | 41666.6667 | 31250 | 8333.3333 | 62.5 | 134166.6667
| Attapeu | 189.5833 | 204.1667 | 2916.6667 | 2187.5 | 583.3333 | 4.375 | 11666.6667
| Bolikhamxai | 81.25 | 87.5 | 1250 | 937.5 | 250 | 1.875 | 6416.6667
| Champasak | 189.5833 | 204.1667 | 2916.6667 | 2187.5 | 583.3333 | 4.375 | 4083.3333
| Houaphan | 108.3333 | 116.6667 | 1666.6667 | 1250 | 333.3333 | 2.5 | 8750
| Khammouane | 379.1667 | 408.3333 | 5833.3333 | 4375 | 1166.6667 | 8.75 | 14583.3333
| Luang Prabang | 81.25 | 87.5 | 1250 | 937.5 | 250 | 1.875 | 7000
| Oudomxai | 27.0833 | 29.1667 | 416.6667 | 312.5 | 83.3333 | 0.625 | 2916.6667
| Phongsaly | 27.0833 | 29.1667 | 416.6667 | 312.5 | 83.3333 | 0.625 | 4083.3333
| Salavan | 243.75 | 262.5 | 3750 | 2812.5 | 750 | 5.625 | 7583.3333
| Savannakhet | 487.5 | 525 | 7500 | 5625 | 1500 | 11.25 | 20416.6667
| Sekong | 162.5 | 175 | 2500 | 1875 | 500 | 3.75 | 7000
| Vientiane | 13.5417 | 14.5833 | 208.3333 | 156.25 | 41.6667 | 0.3125 | 4083.3333
| Vientiane Capital | 13.5417 | 14.5833 | 208.3333 | 156.25 | 41.6667 | 0.3125 | 2916.6667
| Xaisomboun | 27.0833 | 29.1667 | 416.6667 | 312.5 | 83.3333 | 0.625 | 3500
| Xieng Khuang | 677.0833 | 729.1667 | 10416.6667 | 7812.5 | 2083.3333 | 15.625 | 29166.6667
2026 | Total | 6500 | 7000 | 100000 | 75000 | 20000 | 150 | 230000
| Attapeu | 455 | 490 | 7000 | 5250 | 1400 | 10.5 | 20000
| Bolikhamxai | 195 | 210 | 3000 | 2250 | 600 | 4.5 | 11000
| Champasak | 455 | 490 | 7000 | 5250 | 1400 | 10.5 | 7000
| Houaphan | 260 | 280 | 4000 | 3000 | 800 | 6 | 15000
| Khammouane | 910 | 980 | 14000 | 10500 | 2800 | 21 | 25000
| Luang Prabang | 195 | 210 | 3000 | 2250 | 600 | 4.5 | 12000
| Oudomxai | 65 | 70 | 1000 | 750 | 200 | 1.5 | 5000
| Phongsaly | 65 | 70 | 1000 | 750 | 200 | 1.5 | 7000
| Salavan | 585 | 630 | 9000 | 6750 | 1800 | 13.5 | 13000
| Savannakhet | 1170 | 1260 | 18000 | 13500 | 3600 | 27 | 35000
| Sekong | 390 | 420 | 6000 | 4500 | 1200 | 9 | 12000
| Vientiane | 32.5 | 35 | 500 | 375 | 100 | 0.75 | 7000
| Vientiane Capital | 32.5 | 35 | 500 | 375 | 100 | 0.75 | 5000
| Xaisomboun | 65 | 70 | 1000 | 750 | 200 | 1.5 | 6000
| Xieng Khuang | 1625 | 1750 | 25000 | 18750 | 5000 | 37.5 | 50000
2027 | Total | 6500 | 7000 | 100000 | 75000 | 20000 | 150 | 230000
| Attapeu | 455 | 490 | 7000 | 5250 | 1400 | 10.5 | 20000
| Bolikhamxai | 195 | 210 | 3000 | 2250 | 600 | 4.5 | 11000
| Champasak | 455 | 490 | 7000 | 5250 | 1400 | 10.5 | 7000
| Houaphan | 260 | 280 | 4000 | 3000 | 800 | 6 | 15000
| Khammouane | 910 | 980 | 14000 | 10500 | 2800 | 21 | 25000
| Luang Prabang | 195 | 210 | 3000 | 2250 | 600 | 4.5 | 12000
| Oudomxai | 65 | 70 | 1000 | 750 | 200 | 1.5 | 5000
| Phongsaly | 65 | 70 | 1000 | 750 | 200 | 1.5 | 7000
| Salavan | 585 | 630 | 9000 | 6750 | 1800 | 13.5 | 13000
| Savannakhet | 1170 | 1260 | 18000 | 13500 | 3600 | 27 | 35000
| Sekong | 390 | 420 | 6000 | 4500 | 1200 | 9 | 12000
| Vientiane | 32.5 | 35 | 500 | 375 | 100 | 0.75 | 7000
| Vientiane Capital | 32.5 | 35 | 500 | 375 | 100 | 0.75 | 5000
| Xaisomboun | 65 | 70 | 1000 | 750 | 200 | 1.5 | 6000
| Xieng Khuang | 1625 | 1750 | 25000 | 18750 | 5000 | 37.5 | 50000
2028 | Total | 6500 | 7000 | 100000 | 75000 | 20000 | 150 | 230000
| Attapeu | 455 | 490 | 7000 | 5250 | 1400 | 10.5 | 20000
| Bolikhamxai | 195 | 210 | 3000 | 2250 | 600 | 4.5 | 11000
| Champasak | 455 | 490 | 7000 | 5250 | 1400 | 10.5 | 7000
| Houaphan | 260 | 280 | 4000 | 3000 | 800 | 6 | 15000
| Khammouane | 910 | 980 | 14000 | 10500 | 2800 | 21 | 25000
| Luang Prabang | 195 | 210 | 3000 | 2250 | 600 | 4.5 | 12000
| Oudomxai | 65 | 70 | 1000 | 750 | 200 | 1.5 | 5000
| Phongsaly | 65 | 70 | 1000 | 750 | 200 | 1.5 | 7000
| Salavan | 585 | 630 | 9000 | 6750 | 1800 | 13.5 | 13000
| Savannakhet | 1170 | 1260 | 18000 | 13500 | 3600 | 27 | 35000
| Sekong | 390 | 420 | 6000 | 4500 | 1200 | 9 | 12000
| Vientiane | 32.5 | 35 | 500 | 375 | 100 | 0.75 | 7000
| Vientiane Capital | 32.5 | 35 | 500 | 375 | 100 | 0.75 | 5000
| Xaisomboun | 65 | 70 | 1000 | 750 | 200 | 1.5 | 6000
| Xieng Khuang | 1625 | 1750 | 25000 | 18750 | 5000 | 37.5 | 50000
2029 | Total | 6500 | 7000 | 100000 | 75000 | 20000 | 150 | 230000
| Attapeu | 455 | 490 | 7000 | 5250 | 1400 | 10.5 | 20000
| Bolikhamxai | 195 | 210 | 3000 | 2250 | 600 | 4.5 | 11000
| Champasak | 455 | 490 | 7000 | 5250 | 1400 | 10.5 | 7000
| Houaphan | 260 | 280 | 4000 | 3000 | 800 | 6 | 15000
| Khammouane | 910 | 980 | 14000 | 10500 | 2800 | 21 | 25000
| Luang Prabang | 195 | 210 | 3000 | 2250 | 600 | 4.5 | 12000
| Oudomxai | 65 | 70 | 1000 | 750 | 200 | 1.5 | 5000
| Phongsaly | 65 | 70 | 1000 | 750 | 200 | 1.5 | 7000
| Salavan | 585 | 630 | 9000 | 6750 | 1800 | 13.5 | 13000
| Savannakhet | 1170 | 1260 | 18000 | 13500 | 3600 | 27 | 35000
| Sekong | 390 | 420 | 6000 | 4500 | 1200 | 9 | 12000
| Vientiane | 32.5 | 35 | 500 | 375 | 100 | 0.75 | 7000
| Vientiane Capital | 32.5 | 35 | 500 | 375 | 100 | 0.75 | 5000
| Xaisomboun | 65 | 70 | 1000 | 750 | 200 | 1.5 | 6000
| Xieng Khuang | 1625 | 1750 | 25000 | 18750 | 5000 | 37.5 | 50000
2030 | Total (to July 31st) | 3791.6667 | 4083.3333 | 58333.3333 | 43750 | 11666.6667 | 87.5 | 95833.3333
| Attapeu | 265.4167 | 285.8333 | 4083.3333 | 3062.5 | 816.6667 | 6.125 | 8333.3333
| Bolikhamxai | 113.75 | 122.5 | 1750 | 1312.5 | 350 | 2.625 | 4583.3333
| Champasak | 265.4167 | 285.8333 | 4083.3333 | 3062.5 | 816.6667 | 6.125 | 2916.6667
| Houaphan | 151.6667 | 163.3333 | 2333.3333 | 1750 | 466.6667 | 3.5 | 6250
| Khammouane | 530.8333 | 571.6667 | 8166.6667 | 6125 | 1633.3333 | 12.25 | 10416.6667
| Luang Prabang | 113.75 | 122.5 | 1750 | 1312.5 | 350 | 2.625 | 5000
| Oudomxai | 37.9167 | 40.8333 | 583.3333 | 437.5 | 116.6667 | 0.875 | 2083.3333
| Phongsaly | 37.9167 | 40.8333 | 583.3333 | 437.5 | 116.6667 | 0.875 | 2916.6667
| Salavan | 341.25 | 367.5 | 5250 | 3937.5 | 1050 | 7.875 | 5416.6667
| Savannakhet | 682.5 | 735 | 10500 | 7875 | 2100 | 15.75 | 14583.3333
| Sekong | 227.5 | 245 | 3500 | 2625 | 700 | 5.25 | 5000
| Vientiane | 18.9583 | 20.4167 | 291.6667 | 218.75 | 58.3333 | 0.4375 | 2916.6667
| Vientiane Capital | 18.9583 | 20.4167 | 291.6667 | 218.75 | 58.3333 | 0.4375 | 2083.3333
| Xaisomboun | 37.9167 | 40.8333 | 583.3333 | 437.5 | 116.6667 | 0.875 | 2500
| Xieng Khuang | 947.9167 | 1020.8333 | 14583.3333 | 10937.5 | 2916.6667 | 21.875 | 20833.3333
| TOTAL | 32500 | 35000 | 500000 | 375000 | 100000 | 750 | 1150000

## Resources required
Resources required
| 2025* | 2026 | 2027 | 2028 | 2029 | 2030**
Financial (US$m) | 18.75 | 45 | 45 | 45 | 45 | 26.25
National Financial Resources (in kind)
External Funding Requirements (%) | 100 | 100 | 100 | 100 | 100 | 100
Technical
- UNDP support to NRA | bar: 2025* to 2030**
- External support for IMSMA Core (GICHD) | bar: 2025* to 2030**
Personnel (total staff working in the sector) | 4800 | 4800 | 4800 | 4800 | 4800 | 4800
* From 1st August 2025
** To 31st July 2030